## Sheet1
Actions | Steps | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | Outcome | Person In- Charge
Staff training | District level training | [12 empty] | training x2 within 6 months | Quality & Primer unit | bar: 2023-06-01 to 2023-12-01
| Identify champions | [12 empty] | 2 champions from each health clinic (total 16) | Quality & Primer unit | bar: 2023-06-01 to 2024-01-01
| Clinic level training | [12 empty] | Echo training: to cover 80% of staff | MOIC each clinic | bar: 2024-01-01 to 2024-05-01
Revision Incident reporting work flow | Study existing work process | [12 empty] | Find the gap in exsting work process | Quality Unit | bar: 2023-06-01
| Reference with latest circular/ guidelines | [12 empty] | Find the gap in exsting work process | Quality Unit | bar: 2023-06-01
| Create digital platform (google form) and its feasibility | [12 empty] | Transform and translated the manual existing incident reporting form to google form and at the same time ensuring the P&C of data is secured. | Quality Unit/ ICT | bar: 2023-07-01 to 2023-08-01
| Distribution of QR code/link to all clinics | [12 empty] | All clinics need to place the QR code at the staff common areas | Quality Unit/ MOIC | bar: 2023-09-01
| Official instruction of usage newly revised work process from top management | [12 empty] | To standardised the usage of the new incident reporting platform | District Health Officer | bar: 2023-09-01 to 2023-10-01
| Educate staff on new incident reporting work flow | [12 empty] | Staff aware the existing new work flow to report incident | Quality Unit/ MOIC | bar: 2023-10-01 to 2023-12-01
Develop quick reeferences and guidelines | Compilation of latest circular/ guidelines | [12 empty] | Easily accessed by staff | Quality Unit | bar: 2023-06-01 to 2023-07-01
| Create google drive folder | [13 empty] | Quality Unit | bar: 2023-08-01
| Sharing thru WhatsApp group and Google site | [13 empty] | Quality Unit | bar: 2023-09-01 to 2023-11-01
Re-establishment of Patient Safety Committee | Identify relevant units | [12 empty] | Functional committee with clear roles and responsibilities | Quality Unit | bar: 2023-12-01 to 2024-01-01
| Develop organization chart with TOR | [13 empty] | District Health Officer | bar: 2024-01-01
| Meeting | [13 empty] | District Health Officer | bar: 2024-01-01; 2024-05-01
Promotional activities | Appoint technical team | [13 empty] | District Health Officer | bar: 2023-09-01 to 2023-10-01
| Activities proposal | [13 empty] | Promotion team | bar: 2023-11-01 to 2024-01-01
| Patient Safety Day celebration preparation | [13 empty] | Promotion team/ committee | bar: 2024-05-01