## Sheet1
CLINICAL PRACTICE GUIDELINES (CPG) TRAINING WORK PROCESS
CPG TITLE : Management of Retinopathy of Prematurity (Second Edition)
No. | ACTIVITY / TIME | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13
| August 2023 - July 2023 | August | September | October | Nov | Dec | Jan | Feb | Mac | Apr | May | Jun | July | August
1 | Prepare CPG Training Module | bar: Month 1 August to Month 2 September
2 | Conduct Train the Trainers Workshop | bar: Month 3 October
3 | Identifying State Champions for ECO Training | bar: Month 3 October
a) | monioring of ECO training | bar: Month 3 October to Month 7 Feb
Planned
Actual